## Risk Register (Company)
[6 empty] | Risk Assessment |  |  |  | Plan
Code | Date Created | Description | Category | Type | Owner | Likelihood | Impact | Risk Response | Trigger | Mitigation / Enhancement | Contingency | Progress | Status | Date Updated
1 | 25/03/2022 | NDA approval delay, restricting access to the data. | Management | Negative | Miguel Gomes | Very High | Very High | Accept | From both customers and FEUP, we received feedback indicating that the NDA signature process would take an indefinite amount of time. | - Start by developing data-independent features so that we already progress on the prototype without having access to data. - Simulate some data based on the data structure presented in the client slides. | From both customers and FEUP, we received feedback indicating that the NDA signature process would take an indefinite amount of time. | While we waited for access to the data, we prepared the project environment according to the chosen technologies, and started the prototype development. The NDA is now, finally, approved! | Resolved | 13/05/2022
2 | 2022-01-04 | High expertise is needed by the client to maintain or change the product in the future | Customer | Negative | André Malheiro | Medium | High | Mitigate | Customers have informed us that, as our approach uses technologies different from those anticipated by them, we will have to be responsible for facilitating the understanding of our implementation by users of the app so that they can continue its development. | - Continuous development of a maintenance manual and an instructions manual, including critical snippets of code responsible for features; - The team shall follow good programming standards, including code documentation; | If it is not possible to prepare documentation due to lack of time, the team should arrange a meeting with future users of this application to inform them of the most important topics of its usability. |  | Identified | 22/04/2022
3 | 2022-08-04 | LGP Agencies services delay | Dependencies | Negative | Paulo Ribeiro e João Rocha | High | Medium | Mitigate | We were informed of the estimated time for the services by the representatives of these LGP agencies, and we fear that we will not have the products ready before the Review meeting. | - We can start by developing the backend of the application instead. This approach brings the problem that we need the NDA signed to get access to the data. | If the LGP agencies do not comply with our agreements, the team should follow with our own designs instead. | - The development of the backend has already started. - A database technology has been decided and integrated. | Resolved | 20/05/2022
4 | 20/04/2022 | Complex client data might lead to data understanding problems | Technical | Negative | Pedro Azevedo | Very Low | Medium | Avoid | Understanding the client's data can delay the implementation start of the main algorithm. From their explanations, the data seemed complex, suggesting that its comprehension may be difficult. Depending on the delay, the client needs may not be fully met. | - The understanding of the data could be facilitated if we asked the clients to give us simple documentation along with the data, consisting of concise descriptions of the many tables or variables. | - If the clients can't elaborate this documentation, we should invest time to study the data and even arrange meetings with the clients in order to enlighten some existing doubts. | After some analysis on the data, the team concluded that the dataset was not too difficult to understand. There were questions made to the client, but overall this risk does not seem to be very difficult to resolve in the next days. | Resolved | 2022-03-06
5 | 13/05/2022 | Incompletion of MVP at the respective milestone (10/06/2022) | Team | Negative | Entire Team | Very High | Very High | Mitigate | We have only received the client data now, due to the NDA signature delay, and some preoccupations arise since the MVP milestone is close, and we must complete a very complex project in a little time. | The only possible mitigation is hard work by the developers that need to do in 1 sprint what should have been done in 3 or 4. If the team can do it, the MVP will be delivered and the risk will be mitigated. | No contigency as well | All key features have already started to be developed but they are not finished yet. The team is continuously wirking on them in order to finish in time. By 10th June, we managed to complete the MVP, ending this risk. | Resolved | 2022-06-10
6 | 2022-06-10 | Failure of our LGP Challenge presentation | Other | Negative | Entire Team | Low | High | Avoid | We only have a few days to prepare our presentation, which will be very important to our company's image. | - Start preparing the presentation as soon as possible, ensuring it is as interesting as possible. | No contigency as well | - We've already gathered some ideas about what to do in the presentation to capture the audience's attention. | Open | 2022-06-10
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Team member responsible for managing this risk
Note on J2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Triggers, symptoms, and warning signs of risks’ occurrence
Note on K2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: actions to reduce (increase) the probability and/or impact of an adverse risk (opportunity) event to be within acceptable threshold limits
Note on L2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Plan devised for an exceptional risk that, though unlikely, would have catastrophic consequences
Note on M2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Status of the actions

## Risk Matrix
impact
likelihood |  | Very Low | Low | Medium | High | Very High
| Very High | Yellow | Orange | Red | Dark Red | Dark Red
| High | Yellow | Yellow | Orange | Red | Dark Red
| Medium | Green | Yellow | Yellow | Orange | Red
| Low | Green | Green | Yellow | Yellow | Orange
| Very Low | Green | Green | Green | Yellow | Yellow

## data
Risk
Category |  | Type |  | Level | Response |  | Status
Team | Problems with availability of team members, internal communication, ability to work as a team, lack of skills, leadership, etc. | Positive | Opportunity | Very Low | Avoid | Avoid should be used when you want to be sure that the negative risk is not encountered | Identified
Customer | Availability, ease of communication, responsiveness and maturity of customer and other stakeholders. | Negative | Risk | Low | Mitigate | Try to ensure it doesn’t happen | Open
Scope | Complexity, uncertainity, volatility or ignorance of scope, requirements, functionality, application domain or target users. |  |  | Medium | Transfer | Give to someone else like insurance company | Resolved
Dependencies | Dependency of external resources such as APIs, data sets, devices, documentation, etc., wich might not be available or not have the needed quality. |  |  | High | Accept | Accept the risk when you can or you have to
Management | Problems with project estimation, planing, monitoring and control, such as unreliable estimates, difficulty to track progress, difficulty to control changes, etc. |  |  | Very High | Exploit | Use this strategy when you REALLY want the positive risk to happen
Technical | Technical complexity, lack of experience with technologies, imature technologies, uncertainity regarding technical solution. |  |  |  | Enhance | Try to ensure that the positive risk occurs
Other |  |  |  |  | Share | Get a third party involved to try to help you best capture the positive risk
[5 empty] | Accept | Enjoy the benefits of the opportunity